## Your Project Name Here
Task Name | Start Date | End Date | Duration | Predecessors | % Complete | Status | Assigned To | At Risk | Comments
Section 1 - Diagram quiz implementation and test | 2017-07-24 | 2017-08-10 | 14d |  | 0% | Not Started
Sub-task 1 - Install the developing environment and get clear about the requirement | 2017-07-24 | 2017-07-25 | 2d |  | 0% | Not Started | Daming Zhang
Sub-task 2 - Design Diagram quiz and get start to implement basic function | 2017-07-26 | 2017-08-07 | 9d |  | 0% | Not Started | Daming Zhang
Sub-task 3 - Finish implementation and test | 2017-08-08 | 2017-08-10 | 3d |  | 0% | Not Started
Section 2 - Hangman implementation and test | 2017-08-10 | 2017-09-04 | 18d |  | 0% | Not Started
Sub-task 1 - Design and implement the basic function | 2017-08-10 | 2017-08-22 | 9d |  | 0% | Not Started
Sub-task 2 - Design the animation and test | 2017-08-23 | 2017-08-30 | 6d |  | 0% | Not Started
Sub-task 3 - Test the new features and the functionality and usability of Hangman | 2017-08-31 | 2017-09-04 | 3d |  | 0% | Not Started
Section 3 - Chemic element picture implementation and test | 2017-09-05 | 2017-09-19 | 11d |  | 0% | Not Started
Sub-task 1 - Design two type of Chemic element picture quizzes | 2017-09-05 | 2017-09-07 | 3d |  | 0% | Not Started
Sub-task 2 - Implement chemic formula quiz and chemic element quiz | 2017-09-08 | 2017-09-15 | 6d |  | 0% | Not Started
Sub-task 3 - Test both type of chemic picture quizzes | 2017-09-15 | 2017-09-19 | 3d |  | 0% | Not Started
Section 4 - Option Circuit diagram implementation and test | 2017-09-19 | 2017-10-09 | 15d |  | 0 | Not Started
Sub-task 1 - Design two type of Chemic element picture quizzes | 2017-09-19 | 2017-09-20 | 2d |  | 0% | Not Started
Sub-task 2 - Implement chemic formula quiz and chemic element quiz | 2017-09-21 | 2017-10-03 | 9d |  | 0% | Not Started
Sub-task 3 - Test both type of chemic picture quizzes | 2017-10-04 | 2017-10-09 | 4d |  | 0% | Not Started
set up environment later

## Comments
Row 5 | Sub-task 2 Sample discussion... | Todd Jones | 08/30/13 5:13 PM