## Your Project Name Here
Task Name | Start Date | End Date | Duration (day) | Predecessors | % Complete | Status | Assigned To | At Risk | Comments
Section 1 - Diagram quiz implementation and test | 2017-07-29 | 2017-08-10 | 23 |  | 0% | Started
Sub-task 1 - Design Diagram quiz | 2017-07-29 | 2017-07-30 | 1 |  | 100% | Started | Daming Zhang
Sub-task 2 - Write up proposal | 2017-07-30 | 2017-08-01 | 2 |  | 60% | Started | Daming Zhang
Sub-task 3 - Start to implement main functions | 2017-08-01 | 2017-08-11 | 10 |  | 100% | Started | Daming Zhang
Sub-task 4 - Change the requirements and fix bugs | 2017-08-11 | 2017-08-19 | 8 |  | 100% | Started | Daming Zhang
Sub-task 5 - Add new features and fix bugs | 2017-08-19 | 2017-08-29 | 10 |  | 100% | Started | Daming Zhang
Sub-task 6 - Write methodology topic partA | 2017-08-29 | 2017-08-31 | 2 |  | 30% | Started | Daming Zhang
Sub-task 7 - Add QA document for course | 2017-08-31 | 2017-09-01 | 1 |  | 50% | Started | Daming Zhang
Section 2 - Hangman implementation and test | 2017-09-01 | 2017-09-04 | 42 |  | 0% | Started
Sub-task 1 - Design and make a basic demo | 2017-09-01 | 2017-09-03 | 2 |  | 100% | Not Started | Daming Zhang
Sub-task 2 - Implement the basic function | 2017-09-03 | 2017-09-13 | 10 |  | 20% | Not Started | Daming Zhang
Sub-task 3 - Write methodology topic partB | 2017-09-13 | 2017-09-16 | 3 |  | 0% | Not Started | Daming Zhang
Sub-task 4 - Design the animation and test | 2017-09-16 | 2017-09-27 | 11 |  | 10% | Not Started | Daming Zhang
Sub-task 5 - Set up the Diagram quiz and Hangman quiz to Moodle test environment | 2017-09-16 | 2017-09-30 | 14 |  | 0% | Not Started | Daming Zhang
Sub-task 6 - Finish the proposal | 2017-09-27 | 2017-09-29 | 2 |  | 0% | Not Started | Daming Zhang
Sub-task 7 - Test Diagram quiz and Hangman quiz on the Moodle test environment | 2017-09-29 | 2017-10-12 | 13 |  | 0% | Not Started | Daming Zhang
Formulas:
Duration (day) = DAYS([End Date],[Start Date])
Start Date = [End Date, row above]

## Comments
Row 5 | Sub-task 2 Sample discussion... | Todd Jones | 08/30/13 5:13 PM