## Sheet1
Date | Ideal/hrs | Actual/hrs | Spend/hrs
2017-07-29 | 288 | 288 | 22
2017-08-05 | 264 | 266 | 25
2017-08-12 | 240 | 241 | 29
2017-08-19 | 216 | 212 | 26
2017-08-26 | 192 | 186 | 20
2017-09-02 | 168 | 166 | 19
2017-09-09 | 144 | 147 | 29
2017-09-16 | 120 | 118 | 25
2017-09-23 | 96 | 93 | 27
2017-09-30 | 72 | 66 | 32
2017-10-07 | 48 | 34 | 26
2017-10-14 | 24 | 8 | 15
2017-10-21 | 0 | -7 | 0
Formulas:
Date = [Date, row above]+7

## Sheet2
credits | hours
45 | 450 |  | 9 week term 1
industry minimum* | 288 |  | 24 | hours per week = | 12 | weeks
course work hours | 162
- weekly course meeting | 32
= self directed time | 130 | /50% | 2.6 | per mark | 10.8333 | coursework hrs / week
|  |  | 13 | for 5 mark task
| 43.3333 |  | 26 | for 10 mark task
*
must complete hours AND be FINISHED
so start to finish up in the week you hit 288 hours
You will be told that you have 5 working days to finish if you hit 300 hours
You are significantly loosing marks if you exceed 350 hours

## Sheet3
Date | Ideal/hrs | Actual/hrs | Spend/hrs | Achieve Date | Achievement
2017-07-29 | 288 | 288 | 22 | 2017-07-29 | First iteration of proposal to ensured the project was feasible
2017-08-05 | 264 | 266 | 25 | 2017-08-01 | Second iteration of proposal to achieved understanding of the required functionality
2017-08-12 | 240 | 241 | 29 | 2017-08-05 | Diagram project demo under Github version control
2017-08-19 | 216 | 212 | 26 | 2017-08-06 | Demo on the Github web page
2017-08-26 | 192 | 186 | 20 | 2017-08-10 | Gained understanding of some common issues
2017-09-02 | 168 | 166 | 19 | 2017-08-12 | Risk management plan:50 risks identified in notes
2017-09-09 | 144 | 147 | 29 | 2017-08-13 | 8 mail risks analysis
2017-09-16 | 120 | 118 | 25 | 2017-08-16 | QA for course
2017-09-23 | 96 | 93 | 0 | 2017-08-17 | First iteration of Diagram activity demo
2017-09-30 | 72 | 93 | 0 | 2017-08-18 | QA for course
2017-10-07 | 48 | 93 | 0 | 2017-08-24 | Coordinates generator tool achieved
2017-10-14 | 24 | 93 | 0 | 2017-08-28 | Finish developming basic features such as "input" type and "drag" type
2017-10-21 | 0 | 93 | 0 | 2017-08-31 | Finish Implement Diagram and test on local test environment
|  |  |  | 2017-09-06 | Sign off the proposal
|  |  |  | 2017-09-08 | Methodology Essay Part A
|  |  |  | 2017-09-14 | Using JsDoc to generate API for Diagram
|  |  |  | 2017-09-18 | Halfway report cover all topics
|  |  |  | 2017-09-24 | A "Hangman" demo with basic function code
|  |  |  | 2017-09-27 | Fixed CoordianteCreater bugs
|  |  |  | 2017-09-29 | Notes for Risks and XP game for Methodology topic
|  |  |  | 2017-10-02 | Finished "Hangman" with all functions
|  |  |  | 2017-10-08 | Test Diagram and Hangman on Moodle3 environment
|  |  |  | 2017-10-12 | Recreate CoordinateCreater2 tool for Diagram
|  |  |  | 2017-10-15 | Adding new type of Diagram quiz
Formulas:
Date = [Date, row above]+7